## nbnco-rollout-metrics
National Broadband Network – Rollout Information
The data contained in this document reflects NBN Co’s position for the week ending 01 July 2021
Weekly Summary
This weekly report by NBN Co of network rollout progress reflects the Government’s requirements for greater transparency as set out in the Statement of Expectations to NBN Co. This shows rollout progress
as of last Thursday 01 July 2021.
A total of 11,229 additional lots/premises were ready to connect during the week. This included an increase of 3,755 in Brownfield areas, an increase of 3,050 in New Development areas
and an increase of 4,424 premises in fixed wireless and satellite areas.
During the week an additional 7,146 premises had services activated on the network, including 6,586 more on fixed line services and 560 more using satellite and fixed wireless technologies.
Please note “Ready to Connect” includes premises which are temporarily categorised as HFC supply constrained, where our work on the network is complete but in the short term an order cannot be placed
(see here for more information)
| Brownfields |  | New Developments (Greenfields) |  | Satellite |  | Wireless |  | Totals
Week ending | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated
| (A) | (B) | .(C) | (D) | (E) | (F) | (G) | (H) | (K)=(A+C+E+G) | (L)=(B+D+F+H)
ACT | 196757 | 113680 | 30603 | 20368 | 354 | 95 |  | 3 | 227714 | 134146
NSW | 3119408 | 2229262 | 298422 | 209745 | 130990 | 38551 | 166174 | 98702 | 3714994 | 2576260
NT | 68988 | 47966 | 8361 | 5618 | 12564 | 3903 | 5228 | 3043 | 95141 | 60530
QLD | 1944970 | 1381155 | 206628 | 131885 | 96741 | 24826 | 141701 | 78368 | 2390040 | 1616234
SA | 742740 | 520578 | 40942 | 25680 | 33888 | 6566 | 63584 | 31537 | 881154 | 584361
TAS | 213877 | 161432 | 12066 | 6440 | 17760 | 5065 | 40650 | 24134 | 284353 | 197071
VIC | 2544503 | 1811144 | 324812 | 218508 | 75917 | 17691 | 163321 | 99157 | 3108553 | 2146500
WA | 1056552 | 774898 | 107815 | 72145 | 59583 | 14808 | 41424 | 21372 | 1265374 | 883223
2021-07-01 | 9887795 | 7040115 | 1029649 | 690389 | 427797 | 111505 | 622082 | 356316 | 11967323 | 8198325
2021-06-24 | 9884040 | 7035916 | 1026599 | 688002 | 427592 | 111526 | 617863 | 355735 | 11956094 | 8191179
2021-06-17 | 9883183 | 7030966 | 1023930 | 685352 | 427473 | 111436 | 617380 | 355043 | 11951966 | 8182797
2021-06-10 | 9882414 | 7025955 | 1021245 | 683180 | 427223 | 111400 | 617079 | 354489 | 11947961 | 8175024
2021-06-03 | 9881385 | 7020711 | 1018521 | 680755 | 426563 | 111280 | 616530 | 353990 | 11942999 | 8166736
2021-05-27 | 9880691 | 7016642 | 1016376 | 678593 | 426434 | 111313 | 614708 | 353546 | 11938209 | 8160094
2021-05-20 | 9879862 | 7011446 | 1013611 | 676326 | 426257 | 111176 | 614541 | 352909 | 11934271 | 8151857
2021-05-13 | 9879054 | 7009396 | 1011538 | 674406 | 426020 | 111000 | 616079 | 352195 | 11932691 | 8146997
2021-05-06 | 9879330 | 7007426 | 1009384 | 672215 | 425835 | 110843 | 615893 | 351536 | 11930442 | 8142020
2021-04-29 | 9879421 | 7006625 | 1006398 | 670382 | 425718 | 110960 | 615672 | 350940 | 11927209 | 8138907
2021-04-22 | 9878280 | 7002792 | 1003686 | 668478 | 425532 | 110754 | 615062 | 350356 | 11922560 | 8132380
National Broadband Network – Rollout Information
The data contained in this document reflects NBN Co’s position for the week ending 01 July 2021
| Brownfields |  | New Developments (Greenfields) |  | Satellite |  | Wireless
Week ending | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated
| (A) | (B) | .(C) | (D) | (E) | (F) | (G) | (H) | (K)=(A+C+E+G) | (L)=(B+D+F+H)
2021-04-15 | 9876951 | 6996386 | 1000547 | 666170 | 425363 | 110551 | 614699 | 349597 | 11917560 | 8122704
2021-04-08 | 9876106 | 6987390 | 997591 | 663991 | 425135 | 110362 | 614849 | 348692 | 11913681 | 8110435
2021-04-01 | 9875961 | 6982790 | 996227 | 662535 | 425032 | 110388 | 614649 | 348270 | 11911869 | 8103983
2021-03-25 | 9874966 | 6974694 | 992507 | 660740 | 424886 | 110356 | 614069 | 347520 | 11906428 | 8093310
2021-03-18 | 9873858 | 6965756 | 988965 | 658484 | 424771 | 110200 | 613750 | 347090 | 11901344 | 8081530
2021-03-11 | 9873450 | 6954366 | 986320 | 656062 | 424605 | 110000 | 613504 | 346432 | 11897879 | 8066860
2021-03-04 | 9873635 | 6944608 | 982355 | 653944 | 424476 | 109766 | 613241 | 345732 | 11893707 | 8054050
2021-02-25 | 9872702 | 6937400 | 979864 | 652030 | 424325 | 109602 | 612754 | 345095 | 11889645 | 8044127
2021-02-18 | 9871583 | 6926399 | 977844 | 649738 | 424057 | 109398 | 612402 | 344417 | 11885886 | 8029952
2021-02-11 | 9871565 | 6914487 | 975320 | 647082 | 423788 | 109046 | 612170 | 343547 | 11882843 | 8014162
2021-02-04 | 9870876 | 6903003 | 972840 | 644968 | 423392 | 108848 | 611872 | 342848 | 11878980 | 7999667
2021-01-28 | 9870216 | 6893285 | 969926 | 642855 | 438480 | 108796 | 625059 | 341965 | 11903681 | 7986901
2021-01-21 | 9867623 | 6882447 | 967231 | 640962 | 438287 | 108675 | 624754 | 341506 | 11897895 | 7973590
2021-01-14 | 9866924 | 6869368 | 965024 | 638511 | 437990 | 108419 | 624754 | 340665 | 11894692 | 7956963
2021-01-07 | 9867375 | 6857950 | 963512 | 636352 | 437807 | 108178 | 624548 | 339825 | 11893242 | 7942305
2020-12-31 | 9867342 | 6848280 | 963473 | 634553 | 437628 | 108208 | 624289 | 339314 | 11892732 | 7930355
2020-12-24 | 9863609 | 6844144 | 963383 | 633442 | 437561 | 108257 | 624159 | 339319 | 11888712 | 7925162
2020-12-17 | 9856575 | 6828541 | 961322 | 630854 | 437370 | 108154 | 622271 | 338864 | 11877538 | 7906413
2020-12-10 | 9851955 | 6810575 | 958436 | 627913 | 437134 | 107950 | 622420 | 338184 | 11869945 | 7884622
2020-12-03 | 9849315 | 6791601 | 956127 | 625122 | 436977 | 107655 | 622053 | 337365 | 11864472 | 7861743
2018-02-22 | 4807564 | 2969986 | 495565 | 314542 | 425816 | 85997 | 574535 | 221113 | 6303480 | 3591638
2018-02-15 | 4798060 | 2944459 | 493092 | 312354 | 425610 | 85645 | 573569 | 219996 | 6290331 | 3562454
2018-02-08 | 4794217 | 2919123 | 491044 | 310279 | 425345 | 85217 | 573169 | 218883 | 6283775 | 3533502
National Broadband Network – Rollout Information
The data contained in this document reflects NBN Co’s position for the week ending 30 March 2017
|  |  | New Developments (Greenfields) |  |  | Satellite | Wireless
Week ending Day/Month/Year | Premises Serviceable 1 | Premises Activated | Lots/ Premises Passed | Premises Activated |  | Premises Activated | Premises Covered | Premises Activated |  | Premises Activated
| (B) | (D) | .(E) | (F) |  | (G) | (H) | (I) |  | (D+F+G+I)
2016-08-25 | 1867810 | 909253 | 291862 | 180313 |  | 47181 | 429921 | 129186 |  | 1265933
2016-08-18 | 1839949 | 890322 | 289817 | 178870 |  | 46405 | 428361 | 127590 |  | 1243187
2016-08-11 | 1827350 | 871009 | 288507 | 177257 |  | 44726 | 427505 | 125907 |  | 1218899
2016-08-04 | 1811560 | 851930 | 286227 | 175537 |  | 43229 | 426192 | 124282 |  | 1194978
2016-07-28 | 1788090 | 835076 | 284349 | 173964 |  | 42488 | 424519 | 122851 |  | 1174379
2016-07-21 | 1766496 | 818551 | 282843 | 172318 |  | 41183 | 420642 | 121341 |  | 1153393
2016-07-14 | 1752179 | 803592 | 280342 | 170559 |  | 40714 | 420535 | 119922 |  | 1134787
2016-07-07 | 1732999 | 788495 | 279166 | 169110 |  | 39668 | 420693 | 118667 |  | 1115940
2016-06-30 | 1727365 | 774526 | 277839 | 167830 |  | 38764 | 420524 | 117514 |  | 1098634
2016-06-23 | 1586242 | 760453 | 274772 | 166418 |  | 37910 | 402237 | 116333 |  | 1081114
2016-06-16 | 1521654 | 747275 | 272260 | 165086 |  | 37022 | 401697 | 114915 |  | 1064298
2016-06-09 | 1507528 | 736068 | 270756 | 163906 |  | 36113 | 393328 | 113707 |  | 1049794
2016-06-02 | 1481098 | 723439 | 268287 | 162675 |  | 35967 | 392161 | 112366 |  | 1034447
2016-05-26 | 1455698 | 711233 | 265535 | 161478 |  | 35542 | 389836 | 110955 |  | 1019208
2016-05-19 | 1424236 | 698487 | 262656 | 160341 |  | 35118 | 386205 | 109528 |  | 1003474
2016-05-12 | 1410625 | 686209 | 260441 | 159008 |  | 34979 | 381322 | 108002 |  | 988198
2016-05-05 | 1388063 | 673400 | 257938 | 157929 |  | 35010 | 380988 | 106551 |  | 972890
2016-04-28 | 1357232 | 662254 | 256258 | 156920 |  | 34841 | 375593 | 105083 |  | 959098
2016-04-21 | 1329347 | 652181 | 254850 | 156155 |  | 34623 | 373704 | 104058 |  | 947017
2016-04-14 | 1312202 | 639865 | 252999 | 154996 |  | 34758 | 372735 | 102525 |  | 932144
2016-04-07 | 1305626 | 627761 | 250472 | 153795 |  | 34869 | 372288 | 100925 |  | 917350
2016-03-31 | 1297902 | 616076 | 249839 | 152548 |  | 34869 | 369970 | 99455 |  | 902948
2016-03-24 | 1280016 | 608719 | 247935 | 151788 |  | 34959 | 359124 | 98602 |  | 894068
National Broadband Network – Rollout Information
The data contained in this document reflects NBN Co’s position for the week ending 01 July 2021
| Brownfields |  | New Developments (Greenfields) |  | Satellite |  | Wireless
Reporting Date | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated | Ready to Connect | Premises Activated
| (A) | (B) | .(C) | (D) | (E) | (F) | (G) | (H) | (K)=(A+C+E+G) | (L)=(B+D+F+H)
As at 30 June 2011 | (B): 620; (F): 166 | 10575 | 786
As at 30 June 2012 |  | 3364 | 4163 | 503 |  | 9578 | 8885 | 91 | 41908 | 13536
As at 30 June 2013 | 107791 | 20441 | 44028 | 13145 |  | 34640 | 27256 | 1874 | 179075 | 70100
As at 30 June 2014 | 281294 | 105211 | 111116 | 45916 |  | 42948 | 112208 | 16553 | 504618 | 210628
As at 30 June 2015 | 648089 | 298621 | 188591 | 101233 |  | 38288 | 268397 | 47473 | 1105077 | 485615
As at 30 June 2016 | 1727365 | 774526 | 277839 | 167830 | 409959 | 38764 | 420524 | 117514 | 2835687 | 1098634
As at 30 June 2017 | 4113411 | 1935955 | 396147 | 247569 | 418135 | 74928 | 517543 | 184681 | 5445236 | 2443133
As at 30 June 2018 | 5443738 | 3356533 | 553466 | 348926 | 430449 | 90327 | 609913 | 240084 | 7037566 | 4035870
As at 30 June 2019 | 8144120 | 4700610 | 707691 | 451314 | 443154 | 95480 | 659300 | 284683 | 9954265 | 5532087
As at 30 June 2020 | 9806606 | 6275378 | 884875 | 571655 | 431680 | 101258 | 610415 | 319105 | 11733576 | 7267396
As at 30 June 2021 | 9467710 | 7042212 | 1028960 | 690281 | 427766 | 111630 | 622008 | 356280 | 11546444 | 8200403
End of Q3 2018 | 5704995 | 3651107 | 589744 | 376588 | 433917 | 92595 | 618253 | 254400 | 7346909 | 4374690
End of Q4 2018 | 6402795 | 3906962 | 627757 | 401460 | 436580 | 94014 | 632733 | 264530 | 8099865 | 4666966
End of Q1 2019 | 7087529 | 4262972 | 663289 | 428109 | 440257 | 94911 | 643574 | 276068 | 8834649 | 5062060
End of Q2 2019 | 8144120 | 4700610 | 707691 | 451314 | 443154 | 95480 | 659300 | 284683 | 9954265 | 5532087
End of Q3 2019 | 8425725 | 5161015 | 750694 | 479502 | 445924 | 96232 | 666840 | 293136 | 10289183 | 6029885
End of Q4 2019 | 8700479 | 5535664 | 801992 | 508134 | 408954 | 96517 | 579210 | 299318 | 10490635 | 6439633
End of Q1 2020 | 9317402 | 5940490 | 842808 | 540184 | 411137 | 97499 | 589429 | 306963 | 11160776 | 6885136
End of Q2 2020 | 9806606 | 6275378 | 884875 | 571655 | 431680 | 101258 | 610415 | 319105 | 11733576 | 7267396
End of Q3 2020 | 9830582 | 6614967 | 933604 | 604318 | 434823 | 105761 | 618264 | 330311 | 11817273 | 7655357
End of Q4 2020 | 9867342 | 6848280 | 963473 | 634553 | 437628 | 108208 | 624289 | 339314 | 11892732 | 7930355
End of Q1 2021 | 9450688 | 6981718 | 995423 | 662208 | 425018 | 110406 | 614777 | 348115 | 11485906 | 8102447
End of Q2 2021 | 9467710 | 7042212 | 1028960 | 690281 | 427766 | 111630 | 622008 | 356280 | 11546444 | 8200403
As at 30 June 2021 the number of Yet to ready to connect premises that require construction before a customer can order an nbn™ service is 11,677 (QLD: 2,300, NSW: 6,901, ACT: 102, VIC: 1,222, TAS: 0, SA: 41, WA: 1,111, NT: 0).
Ready to connect: A premises is ready to connect when an nbn™ service order can be placed, and the service can be connected within an area that has been declared ready for service, and in the case of premises which are temporarily categorised as HFC supply constrained, where our work on the network is complete but in the short term an order cannot be placed.
Yet to ready to connect: These are premises that require construction work before a service can be ordered which may or may not be within a location declared ready for service. These do not include premises within new development locations nor premises which are temporarily categorised as HFC supply constrained where our work on the network is complete but in the short term an order cannot be placed.
Premises activated: Refers to premises which have an active service installed.
Variations in number from week to week reflect the modular construction program. The construction program is completed in blocks, so variations may occur. Following completion of the construction process
passing premises in the streets, further validation of address data is undertaken of the ‘as built’ network against estimates obtained from national address data. There may be some fluctuation in numbers from
week to week as a result. Note, as at 20 May 2021 we have removed the definition for 'Not yet ready to connect' and 'RFS area' and added a new definition for 'Yet to ready to connect'.