## IMEA
Component | Life_cycle | Activities | Impact_Mode | Effects | Stressors | Lo_Sev | Hi_Sev | Impact_Causes | Lo_Lik | Hi_Lik | Current_Controls | Lo_Det | Hi_Det | Lo_RPN | Hi_RPN | Lo_RS | Hi_RS
Wells | Decomissioning | Pressure concrete completion | Incomplete seal | GW quality, change in GW pressure | TDS, Hydrocarbons, change in GW pressure | 3 | 7 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2.5 | -0.5 | Australian standard; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4.5 | 3 | 11 | 0.5 | 6.5
Wells | Production | Groundwater monitoring bore construction or expansion | Incomplete/compromised cementing/casing (linking aquifers) | GW composition, GW quality | GW composition, Hydrocarbons | 3 | 4 | Incomplete grouting | -0.5 | 0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 2 | 3 | 4.5 | 7.5 | 2.5 | 4.5
Wells | Construction | Groundwater monitoring bore construction | Incomplete/compromised cementing/casing (linking aquifers) | GW composition, GW quality | GW composition, Hydrocarbons | 3 | 4 | Incomplete grouting | -0.5 | 0 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 2 | 3 | 4.5 | 7 | 2.5 | 4
Wells | Construction | Cementing and casing | Incomplete/compromised cementing/casing (linking aquifers) | GW quality | GW composition, Hydrocarbons | 3 | 7 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -0.5 | 0 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 2 | 3.5 | 4.5 | 10.5 | 2.5 | 7
Wells | Construction | Cementing and casing | Incomplete/compromised cementing/casing (gas leakage) | GW quality | TDS, Hydrocarbons | 3 | 5 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1 | 0 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 2 | 3.5 | 4 | 8.5 | 2 | 5
Wells | Decomissioning | Pressure concrete durability | Seal integrity loss | GW quality | TDS, Hydrocarbons, change in GW pressure | 3 | 7 | Inevitable, Deliberate | -2.5 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 4.5 | 4.5 | 5 | 10 | 0.5 | 5.5
Wells | Construction | Groundwater monitoring bore construction | Spillage | SW quality | Hydrocarbons, TDS, Drilling fluids, Drilling mud products | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1.5 | 0 | Careful handling; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 4 | 1.5 | 4
Wells | Construction | Pump and well head installation | Spillage | SW quality | Hydrocarbons, TDS, Drilling fluids, Drilling mud products | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1.5 | 0 | Careful handling; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 4 | 1.5 | 4
Wells | Construction | Materials delivery and storage | Spillage: on site | SW quality | Drilling mud products, Cement, Hydrocarbons | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0.5 | Careful handling; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 4.5 | 2.5 | 4.5
Wells | Decomissioning | Materials delivery and storage | Spillage: on site | SW quality | Hydrocarbons | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1 | -0.5 | Careful handling; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1.5 | 3.5 | 2 | 3.5
Wells | Work-over | Materials delivery and storage | Spillage: on site | SW quality | Hydrocarbons | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1 | -0.5 | Careful handling; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1.5 | 3.5 | 2 | 3.5
Wells | Construction | Hydraulic fracturing concentrate delivery | Spillage: prior to dilution on site | SW quality | Hydrocarbons, TDS, Hydraulic fracturing chemicals | 3 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1 | 0 | Careful handling; Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1.5 | 5 | 2 | 5
Roads and infrastructure | Construction | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Disruption to natural surface water course (e.g. creek crossing) | SW flow | SW flow | 4 | 7 | Inevitable, Deliberate | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2.5 | 7 | 3 | 7
Roads and infrastructure | Exploration and appraisal | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Disruption to natural surface water course (e.g. creek crossing) | SW flow | SW flow | 3 | 4 | Inevitable, Deliberate | 0 | 1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2.5 | 5 | 3 | 5
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Temporary disruption to natural surface water course (e.g. sandbagging a creek to lay pipe) | SW flow | SW flow | 3 | 4 | Inevitable, Deliberate | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 3.5 | 1.5 | 3.5
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Temporary disruption to natural surface water course (e.g. sandbagging a creek to lay pipe) | SW flow | SW flow | 3 | 4 | Inevitable, Deliberate | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 3.5 | 1.5 | 3.5
Roads and infrastructure | Production | Operation access roads and easements (e.g. for drilling rigs and equipment) | Disruption to natural surface water course (e.g. creek crossing) | SW flow | SW flow | 3 | 5 | Inevitable, Deliberate | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1.5 | 5 | 2 | 5
Roads and infrastructure | Construction | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 4 | 6 | Diverting site/corridor drain line | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 3 | 9 | 3 | 6
Roads and infrastructure | Exploration and appraisal | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | 0 | 1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 1.5 | 3 | 6.5 | 3 | 5
Roads and infrastructure | Production | Operation access roads and easements (e.g. for drilling rigs and equipment) | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 1.5 | 6.5 | 1.5 | 3.5
Wells | Construction | Hydraulic fracturing | Changing target aquifer properties (physical or chemical) | Aquifer properties | Aquifer properties | 3 | 5 | Inevitable, Deliberate | -0.5 | 0.5 | Deliberate | 0 | 1 | 2.5 | 6.5 | 2.5 | 5.5
Wells | Construction | Hydraulic fracturing | Contaminate target aquifer (chemical) | GW quality | Hydraulic fracturing chemicals | 3 | 5 | Inevitable, Deliberate | 1 | 1.5 | Deliberate | 0 | 1 | 4 | 7.5 | 4 | 6.5
Roads and infrastructure | Construction | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 5 | Corridor/site vegetation removal | -0.5 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 3.5 | 8 | 3.5 | 5.5
Roads and infrastructure | Production | Operation access roads and easements (e.g. for drilling rigs and equipment) | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 4 | Corridor/site vegetation removal | -0.5 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 2.5 | 7 | 2.5 | 4.5
Roads and infrastructure | Exploration and appraisal | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 4 | Corridor/site vegetation removal | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Wells | Construction | Pump and well head installation | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 8 | Corridor/site vegetation removal | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1.5 | 7.5 | 1.5 | 7.5
Processing | Construction | Hypersaline brine ponds | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 6 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 3 | 6 | 3 | 6
Wells | Construction | Groundwater monitoring bore construction | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 5 | Corridor/site vegetation removal | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1.5 | 4.5 | 1.5 | 4.5
Roads and infrastructure | Construction | Accommodation, administration, workshop, depots, service facilities | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 4 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 2 | 4 | 2 | 4
Wells | Construction | Site preparation | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 4 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 2 | 4 | 2 | 4
Wells | Exploration and appraisal | Site preparation | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 4 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 2 | 4 | 2 | 4
Roads and infrastructure | Exploration and appraisal | Temporary Accommodation, administration, workshop, depots, service facilities | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 4 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 2 | 6.5 | 2 | 4
Roads and infrastructure | Production | Accommodation, administration, workshop, depots, service facilities | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 3 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 2 | 3 | 2 | 3
Processing | Construction | Gas compression stations | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 5 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 3 | 5 | 3 | 5
Processing | Construction | Gas processing plant | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 5 | Corridor/site vegetation removal | -2 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 2 | 5 | 2 | 5
Processing | Construction | Gas-gathering pipeline networks | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 5 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 3 | 5 | 3 | 5
Processing | Construction | Power generation facility (for processing plant) | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 5 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 3 | 5 | 3 | 5
Wells | Construction | Drilling and logging | Localised watertable reduction | change in GW pressure | change in GW pressure | 3 | 4 | Number of drilling control issues | -3 | -2.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0.5 | 1 | 0.5 | 2.5 | 0 | 1.5
Wells | Exploration and appraisal | Drilling and coring | Very localised watertable reduction | change in GW pressure | change in GW pressure | 3 | 4 | Number of drilling control issues | -2.5 | -2.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0.5 | 3 | 1 | 4.5 | 0.5 | 1.5
Wells | Exploration and appraisal | Drilling and coring | Imbalance of mud pressure between well and aquifer | GW quality | TSS, Drilling mud products, TDS | 3 | 5 | Number of drilling control issues | -1.5 | 1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0.5 | 1 | 6.5 | 1.5 | 6
Wells | Construction | Drilling and logging | Imbalance of mud pressure between well and aquifer | GW quality | TSS, Drilling mud products, TDS | 3 | 5 | Number of drilling control issues | -1.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0.5 | 1 | 5.5 | 1.5 | 5
Wells | Construction | Hydraulic fracturing | Changing non-target aquifer properties (physical or chemical) | Aquifer properties | Aquifer properties | 5 | 6 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 1.5 | 2.5 | 4.5 | 7.5 | 3 | 5
Wells | Construction | Perforation | Miss perforation target and connect aquifers through the well | GW composition, GW quality | GW composition, Hydrocarbons | 4 | 7 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0.5 | 1 | 5.5 | 1 | 5
Wells | Construction | Perforation | Miss perforation target and depressurise aquifers | change in GW pressure, GW quality | change in GW pressure | 4 | 7 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -3 | -2.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4 | 3.5 | 8.5 | 1 | 4.5
Wells | Construction | Hydraulic fracturing | Contaminate non-target aquifer (chemical) | GW quality | Hydraulic fracturing chemicals | 4 | 7 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -3 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4 | 3.5 | 10 | 1 | 6
Wells | Construction | Hydraulic fracturing | Connecting aquifers | GW composition, GW quality, change in GW pressure | GW composition, Hydrocarbons | 4 | 7 | Incomplete reservoir knowledge, too much pressure | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4 | 3.5 | 9.5 | 1 | 5.5
Wells | Exploration and appraisal | Abandonment | Bore leakage between aquifers | GW composition, GW quality, change in GW pressure | GW composition, Hydrocarbons | 3 | 6 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 2.5 | 4 | 3.5 | 9.5 | 1 | 5.5
Wells | Exploration and appraisal | Abandonment | Bore leakage to surface | SW quality | SW composition, Hydrocarbons | 3 | 6 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 2.5 | 4 | 3.5 | 9 | 1 | 5
Wells | Production | Untreated co-produced water storage, processing and disposal (pilot stage only) | Leaching from storage ponds | GW quality | TDS, Chemicals | 3 | 6 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2 | 3.5 | 3.5 | 9.5 | 1.5 | 6
Wells | Production | Untreated co-produced water storage, processing and disposal (pilot stage only) | Dam failure | SW quality, GW quality | TDS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 4 | 6 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 4 | 1 | 4
Roads and infrastructure | Exploration and appraisal | Fuel and oil | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Exploration and appraisal | Power and communications | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Exploration and appraisal | Temporary Accommodation, administration, workshop, depots, service facilities | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Processing | Production | Hypersaline brine ponds | Containment failure | SW quality, GW quality | TSS, TDS, pH, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 8 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Natural disaster (e.g. bushfire, flooding, earthquake) | -2.5 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | -0.5 | 0 | 6.5 | 0.5 | 7
Processing | Production | Brine storage ponds, pumps and water disposal pipelines | Containment failure | SW quality, GW quality | TSS, TDS, pH, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 6 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Natural disaster (e.g. bushfire, flooding, earthquake) | -2.5 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | -0.5 | 0 | 4.5 | 0.5 | 5
Processing | Production | Treated water pond | Containment failure | SW quality, GW quality | TSS, TDS, pH, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 5 | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Natural disaster (e.g. bushfire, flooding, earthquake) | -2.5 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | -0.5 | 0 | 3.5 | 0.5 | 4
Processing | Production | Brine storage ponds, pumps and water disposal pipelines | Leaking | SW quality, GW quality | TSS, TDS, pH, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 5 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4 | 3.5 | 8.5 | 1 | 4.5
Processing | Production | Hypersaline brine ponds | Leaking | SW quality, GW quality | TSS, TDS, pH, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 5 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4 | 3.5 | 8.5 | 1 | 4.5
Processing | Production | Treated water pond | Leaking | SW quality, GW quality | TSS, TDS, pH, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 4 | 3.5 | 7.5 | 1 | 3.5
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 6 | Corridor/site vegetation removal | -1 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 3 | 9 | 3 | 6.5
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 6 | Corridor/site vegetation removal | -1 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 3 | 9 | 3 | 6.5
Processing | Construction | Treated water pond | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 4 | 6 | Diverting site/corridor drain line | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 3 | 9 | 3 | 6
Processing | Construction | Brine storage ponds, pumps and water disposal pipelines | Disruption of natural surface drainage | SW volume, SW quality, GW quantity | TSS, SW flow, GW flow | 4 | 6 | Diverting site/corridor drain line | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 3 | 9 | 3 | 6
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Disruption of natural surface drainage | SW volume, SW quality, GW quantity | TSS, SW flow, GW flow | 3 | 7 | Incidental to vegetation removal and compaction in pipeline corridor | 0 | 1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3.5 | 3 | 11.5 | 3 | 8
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Disruption of natural surface drainage | SW volume, SW quality, GW quantity | TSS, SW flow, GW flow | 4 | 7 | Incidental to vegetation removal and compaction in pipeline corridor | -0.5 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3.5 | 3.5 | 11 | 3.5 | 7.5
Processing | Construction | Brine storage ponds, pumps and water disposal pipelines | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 6 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 3 | 6 | 3 | 6
Processing | Construction | Treated water pond | Soil erosion following heavy rainfall | SW quality | TSS | 4 | 6 | Corridor/site vegetation removal | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 3 | 6 | 3 | 6
Wells | Construction | Surface water and mud storage and evaporation | Overflow and/or loss of containment | SW quality, GW quality | TSS, Drilling mud products, TDS | 4 | 6 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 6 | 2.5 | 6
Wells | Exploration and appraisal | Surface water and mud storage and evaporation | Overflow and/or loss of containment | SW quality, GW quality | TSS, Drilling mud products, TDS | 3 | 6 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 6 | 1.5 | 6
Processing | Production | Fuel and oil storage facilities | Spillage | SW quality, GW quality | Hydrocarbons, Pollutants (e.g. metals/trace elements/sulfides/phosphorous), Chemicals | 3 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 4.5 | 1.5 | 4.5
Processing | Decomissioning | Process production plant | Spillage | SW quality, GW quality | Hydrocarbons, Pollutants (e.g. metals/trace elements/sulfides/phosphorous), Chemicals | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 1 | 3.5 | 1.5 | 3.5
Wells | Exploration and appraisal | Materials delivery and storage | Spillage | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 4.5 | 2.5 | 4.5
Processing | Production | Materials delivery and storage | Spillage | SW quality, GW quality | TSS, Drilling mud products, TDS | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 4.5 | 2.5 | 4.5
Roads and infrastructure | Construction | Sewage treatment and disposal | Spillage: e.g. of sewage | SW quality | Organic pollutants | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 2 | 1 | 2
Roads and infrastructure | Decomissioning | Sewage treatment and disposal | Spillage: e.g. of sewage | SW quality | Organic pollutants | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 2 | 1 | 2
Roads and infrastructure | Production | Sewage treatment and disposal | Spillage: e.g. of sewage | SW quality | Organic pollutants | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 2 | 1 | 2
Roads and infrastructure | Construction | Accommodation, administration, workshop, depots, service facilities | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Construction | Fuel and oil | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Construction | Power and communications | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Decomissioning | Fuel and oil | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Production | Accommodation, administration, workshop, depots, service facilities | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Production | Fuel and oil | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Roads and infrastructure | Production | Power and communications | Spillage: e.g. diesel | SW quality, GW quality | Hydrocarbons | 3 | 3 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -0.5 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 2 | 3 | 2.5 | 3
Wells | Construction | Remediation | Mud spillage and poor rubbish disposal | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1.5 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | -0.5 | -0.5 | 1 | 3 | 1.5 | 3.5
Wells | Exploration and appraisal | Site clean-up and rehabilitation | Mud and drill cutting spillage | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -1.5 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | -0.5 | -0.5 | 1 | 3 | 1.5 | 3.5
Wells | Construction | Drill cutting disposal | Surface water contamination | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1.5 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 3 | 4 | 4.5 | 7.5 | 1.5 | 3.5
Wells | Exploration and appraisal | Drill cutting disposal | Surface water contamination | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 3 | 4 | 4 | 7 | 1 | 3
Wells | Work-over | Waste disposal | Surface water contamination | SW quality | TSS, TDS | 3 | 4 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1.5 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 3 | 4 | 4.5 | 7.5 | 1.5 | 3.5
Wells | Exploration and appraisal | Drill stem testing (extraction) | Recovered fluid disposal | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Inappropriate disposal; Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | -0.5 | 0 | 0.5 | 3 | 1 | 3
Wells | Exploration and appraisal | Slug testing (injection) | Recovered fluid disposal | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Inappropriate disposal; Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | -0.5 | 0 | 0.5 | 3 | 1 | 3
Wells | Construction | Groundwater monitoring bore construction | Cuttings disposal | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Inappropriate disposal | -2 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning); Good design/monitoring/management (e.g. staff training) | -0.5 | 0 | 0.5 | 3.5 | 1 | 3.5
Wells | Construction | Hydraulic fracturing fluid injection and disposal | Spillage and/or inappropriate disposal | SW quality | Hydrocarbons, TDS, Hydraulic fracturing chemicals | 3 | 4 | Inappropriate disposal; Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -1 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning); Good design/monitoring/management (e.g. staff training) | -0.5 | 0 | 1.5 | 3.5 | 2 | 3.5
Wells | Construction | Drill stem testing (extraction) | Recovered fluid disposal | SW quality | TSS, Drilling mud products, TDS | 3 | 4 | Inappropriate disposal; Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -0.5 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning); Good design/monitoring/management (e.g. staff training) | -0.5 | 0 | 0.5 | 3.5 | 1 | 3.5
Wells | Exploration and appraisal | Pump testing | Reduction in pressure head | change in GW pressure | change in GW pressure | 3 | 4 | Inevitable, Deliberate | -0.5 | 0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 1 | 2.5 | 5.5 | 2.5 | 4.5
Processing | Production | Gas-gathering pipeline networks | Pipeline failure | SW quality | Hydrocarbons | 3 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 1 | 6.5 | 1 | 4
Pipelines | Production | Trunk gas pipelines and associated easements (processing plant to town) | Pipe failure | SW quality | Hydrocarbons | 3 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 1 | 6.5 | 1 | 4
Pipelines | Production | Gas and water-gathering pipeline networks (well to processing plant) | Pipe failure | SW quality, SW flow | TDS, Hydrocarbons | 3 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 2.5 | 1 | 6.5 | 1 | 4
Processing | Decomissioning | Process production plant | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous), Hydrocarbons, Chemicals | 3 | 4 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 3 | 1 | 3
Pipelines | Production | Gas and water-gathering pipeline networks (well to processing plant) | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous), Hydrocarbons, Chemicals | 4 | 6 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Natural disaster (e.g. bushfire, flooding, earthquake) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 4 | 1 | 4
Processing | Production | Fuel and oil storage facilities | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous), Hydrocarbons, Chemicals | 3 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Natural disaster (e.g. bushfire, flooding, earthquake) | -2.5 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0 | 3.5 | 0.5 | 3.5
Processing | Production | Power generation facility (for processing plant) | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure); Natural disaster (e.g. bushfire, flooding, earthquake) | -2.5 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0 | 2.5 | 0.5 | 2.5
Processing | Production | Gas processing plant | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 4 | 6 | Ignition following pipe failure; Natural disaster (e.g. bushfire, flooding, earthquake) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 4 | 1 | 4
Pipelines | Production | Trunk gas pipelines and associated easements (processing plant to town) | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 4 | 6 | Ignition following pipe failure; Natural disaster (e.g. bushfire, flooding, earthquake) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 4 | 1 | 4
Processing | Production | Gas compression stations | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 4 | 5 | Ignition following pipe failure; Natural disaster (e.g. bushfire, flooding, earthquake) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | 0.5 | 3 | 1 | 3
Processing | Production | Gas-gathering pipeline networks | Fire | SW quality, GW quality | TSS, Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Ignition following pipe failure; Natural disaster (e.g. bushfire, flooding, earthquake) | -3 | -2 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | -0.5 | 2 | 0 | 2
Wells | Exploration and appraisal | Slug testing (injection) | Fluid loss to aquifer | GW composition | GW composition | 3 | 3 | Number of drilling control issues | 1.5 | 2 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | -0.5 | -0.5 | 4 | 4.5 | 4.5 | 5
Processing | Production | Gas compression stations | Spillage | NA | [6 empty] | Plant is bunded |  |  | 0 | 0 | 0 | 0
Processing | Production | Gas processing plant | Spillage | NA | [6 empty] | Plant is bunded |  |  | 0 | 0 | 0 | 0
Wells | Production | Water and gas extraction | Aquifer depressurisation | GW flow (reduction) | change in GW pressure | 4 | 7 | Production of water | -1 | 2 | Regulations (e.g. abandonment practice, irrigation management practice, logging practice, disposal practice, waste disposal, bore construction standards and post-cement logging, guidelines for slug testing planning) | 1 | 2.5 | 4 | 11.5 | 3 | 9
Roads and infrastructure | Construction | Accommodation, administration, workshop, depots, service facilities | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1.5 | 3.5 | 1.5 | 3.5
Wells | Exploration and appraisal | Site preparation | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1.5 | 3.5 | 1.5 | 3.5
Roads and infrastructure | Production | Accommodation, administration, workshop, depots, service facilities | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1.5 | 3.5 | 1.5 | 3.5
Roads and infrastructure | Exploration and appraisal | Temporary Accommodation, administration, workshop, depots, service facilities | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 3 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1.5 | 2.5 | 1.5 | 2.5
Processing | Construction | Gas-gathering pipeline networks | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 3 | 7 | Diverting site/corridor drain line | 0 | 1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3.5 | 3 | 11.5 | 3 | 8
Processing | Construction | Gas processing plant | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 4 | 6 | Diverting site/corridor drain line | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 3 | 9 | 3 | 6
Processing | Construction | Hypersaline brine ponds | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 4 | 6 | Diverting site/corridor drain line | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 3 | 9 | 3 | 6
Processing | Construction | Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc) | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 4 | 6 | Diverting site/corridor drain line | -1 | 0 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 3 | 9 | 3 | 6
Processing | Construction | Gas compression stations | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 1.5 | 6.5 | 1.5 | 3.5
Processing | Construction | Power generation facility (for processing plant) | Disruption of natural surface drainage | SW volume, SW quality | TSS, SW flow | 3 | 4 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 1.5 | 6.5 | 1.5 | 3.5
Processing | Construction | Fuel and oil storage facilities | Disruption of natural surface drainage | SW volume, SW quality, GW quantity | TSS, SW flow, GW flow | 3 | 3 | Diverting site/corridor drain line | -1.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3 | 1.5 | 5.5 | 1.5 | 2.5
Wells | Production | Water and gas extraction | Aquifer depressurisation (non-target, non-reservoir) | change in GW pressure | change in GW pressure | 4 | 8 | Aquitard leaks | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 3 | 4 | 5 | 11 | 2 | 7
Wells | Production | Water and gas extraction | Aquifer depressurisation (coal seam) | change in GW pressure | change in GW pressure | 7 | 8 | Inevitable, Deliberate | 2 | 2.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0.5 | 9 | 11 | 9 | 10.5
Wells | Production | Water and gas extraction | Subsidence | SW directional characteristics | Subsidence | 3 | 6 | Depressurisation | -2.5 | -0.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2 | 3 | 2.5 | 8.5 | 0.5 | 5.5
Wells | Production | Water and gas extraction | Aquifer depressurisation (fault-mediated) | change in GW pressure | change in GW pressure | 5 | 7 | Fault open or opening | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 2.5 | 3.5 | 5.5 | 9.5 | 3 | 6
Wells | Construction | Site preparation | Disruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 5 | Diverting site/corridor drain line | -1 | 1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 2 | 6 | 2 | 6
Processing | Construction | Brine storage ponds, pumps and water disposal pipelines | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Processing | Construction | Gas processing plant | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Processing | Construction | Hypersaline brine ponds | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Processing | Construction | Treated water pond | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Processing | Construction | Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Processing | Decomissioning | Process production plant | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 3 | 1 | 3
Roads and infrastructure | Construction | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Processing | Construction | Gas compression stations | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Processing | Construction | Gas-gathering pipeline networks | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Processing | Construction | Power generation facility (for processing plant) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Wells | Construction | Site preparation | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Roads and infrastructure | Exploration and appraisal | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Wells | Exploration and appraisal | Ground-based geophysics | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | -0.5 | 2.5 | 0 | 2.5
Wells | Exploration and appraisal | Site preparation | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Wells | Work over | Site preparation | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 4 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 2.5 | 0 | 2.5
Processing | Production | Staff movement and activities | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 1 | 2 | 1 | 2
Roads and infrastructure | Construction | Accommodation, administration, workshop, depots, service facilities | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 1.5 | 0 | 1.5
Processing | Construction | Fuel and oil storage facilities | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 1.5 | 0 | 1.5
Wells | Exploration and appraisal | Surface core testing | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | -0.5 | 0 | -0.5 | 1.5 | 0 | 1.5
Roads and infrastructure | Exploration and appraisal | Temporary Accommodation, administration, workshop, depots, service facilities | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 1.5 | 0 | 1.5
Roads and infrastructure | Production | Accommodation, administration, workshop, depots, service facilities | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 1.5 | 0 | 1.5
Roads and infrastructure | Production | Operation access roads and easements (e.g. for drilling rigs and equipment) | Impacts of ground support staff | SW quality | Pollutants (e.g. metals/trace elements/sulfides/phosphorous) | 3 | 3 | Litter, spills | -3 | -1.5 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 0 | 0 | 1.5 | 0 | 1.5
Wells | Construction | Horizontal drilling | Accidental intersection of aquifer | GW quality, change in GW pressure | change in GW pressure, TDS, TSS | 4 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 1 | 2 | 5 | 2 | 4
Wells | Construction | Horizontal drilling | Accidental intersection of fault | GW quality, change in GW pressure | change in GW pressure, TDS, TSS | 4 | 5 | Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | -2 | -1 | Good design, monitoring, management (e.g. site selection, erosion control, engineering works, formation knowledge, monitor temp and water, pipe inspection, staff training) | 0 | 3.5 | 2 | 7.5 | 2 | 4
Wells | Exploration and appraisal | Ground-based geophysics | Soil erosion following heavy rainfall | SW quality | TSS | 3 | 5 | Corridor/site vegetation removal | -3 | -0.5 | Use existing tracks where possible | 0 | 0 | 0 | 4.5 | 0 | 4.5
Wells | Exploration and appraisal | Ground-based geophysics | Interruption of natural surface drainage | SW directional characteristics, SW volume, SW quality | TSS, SW flow | 3 | 4 | Interrupting ephemeral water courses | -3 | -2 | Use existing tracks where possible | 0 | 3 | 0 | 5 | 0 | 2
Wells | Construction | Drilling and logging | Accidental intersection of artesian aquifer | change in GW pressure | change in GW pressure |  |  | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | [5 empty] | 0 | 0 | 0 | 0
Wells | Exploration and appraisal | Drilling and coring | Accidental intersection of artesian aquifer | change in GW pressure | change in GW pressure |  |  | Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | [5 empty] | 0 | 0 | 0 | 0
Processing | Decomissioning | Process production plant | Incomplete removal of concrete base | SW flow, GW recharge | NA | [8 empty] | 0 | 0 | 0 | 0
Processing | Construction | Brine storage ponds, pumps and water disposal pipelines | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Construction | Cementing and casing | Cement interaction with aquifer (leaching Ca(OH)2) | NA | [9 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Construction | Construction of access roads and easements (e.g. for drilling rigs and equipment) | Dust suppression | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Disruption to SW/GW connectivity - due to backfill, soil compaction | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Fuel and oil storage facilities | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Disruption to SW/GW connectivity - due to backfill, soil compaction | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Gas compression stations | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Gas processing plant | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Gas-gathering pipeline networks | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Construction | Groundwater monitoring bore construction | Disruption of natural surface drainage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Construction | Groundwater monitoring bore construction | Impacts of ground support staff | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Cuttings disposal | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Disruption of natural surface drainage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Impacts of ground support staff | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Soil erosion following heavy rainfall | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Construction | Horizontal drilling | Accidental intersection of existing bore | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Hypersaline brine ponds | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Power generation facility (for processing plant) | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Construction | Pump and well head installation | Disruption of natural surface drainage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Construction | Pump and well head installation | Impacts of ground support staff | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Disruption to SW/GW connectivity - due to backfill, soil compaction | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Treated water pond | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Disruption to SW/GW connectivity - due to backfill, soil compaction | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc) | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Decomissioning | Gas and water-gathering pipeline networks (well to processing plant) | Pipe corossion and leaching | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Decomissioning | Trunk gas pipelines and associated easements (processing plant to town) | Pipe corossion and leaching | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Production | Gas and water-gathering pipeline networks (well to processing plant) | Pressurize gas pipe to remove water plug | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Gas compression stations | Equipment failure | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Gas processing plant | Equipment failure | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Groundwater monitoring bore construction or expansion | Cuttings disposal | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Groundwater monitoring bore construction or expansion | Disruption of natural surface drainage | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Groundwater monitoring bore construction or expansion | Impacts of ground support staff | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Groundwater monitoring bore construction or expansion | Soil erosion following heavy rainfall | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Groundwater monitoring bore construction or expansion | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Production | Operation access roads and easements (e.g. for drilling rigs and equipment) | Dust suppression | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Power generation facility (for processing plant) | Spillage | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Discharge to river (via first or third party) | NA | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Discharge to river following heavy rainfall | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Untreated co-produced water storage, processing and disposal (pilot stage only) | Discharge to river | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Untreated co-produced water storage, processing and disposal (pilot stage only) | Discharge to river following heavy rainfall | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Water and gas extraction | Aquifer pressurisation (fault-mediated) | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Work-over | Water injection | Adds to co-produced water | NA | [9 empty] | 0 | 0 | 0 | 0
Wells | Production | Water and gas extraction | Aquifer depressurisation (aquitard-absent) | NA | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Disruption of natural surface drainage | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Impacts of ground support staff | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Intersection of GW via directional drilling under river | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Soil erosion following heavy rainfall | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Spillage | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Temporary disruption to natural surface water course (e.g. sandbagging a creek to lay pipe) | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Gas and water-gathering pipeline networks (well to processing plant) | Intersection of GW via directional drilling under river | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Groundwater extraction | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Groundwater supply bore | Incomplete/compromised cementing/casing (linking aquifers) | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Disruption of natural surface drainage | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Impacts of ground support staff | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Intersection of GW via directional drilling under river | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Soil erosion following heavy rainfall | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Spillage | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Treated co-produced water pipelines and pumps | Temporary disruption to natural surface water course (e.g. sandbagging a creek to lay pipe) | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Construction | Trunk gas pipelines and associated easements (processing plant to town) | Intersection of GW via directional drilling under river | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Construction | Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc) | Soil erosion following heavy rainfall | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Decomissioning | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Pipe corossion and leaching | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Decomissioning | Treated co-produced water pipelines and pumps | Pipe corossion and leaching | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Production | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town) | Pipe failure | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Groundwater supply bore | Groundwater extraction | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Extracting river water for shandying | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Increase discharge to rivers following irrigation | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Raise watertable following irrigation | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Soil chemistry changes following irrigation | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated co-produced water disposal | Soil salt mobilisation following irrigation | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Pipelines | Production | Treated co-produced water pipelines and pumps | Pipe failure | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Treated water disposal | Reinjection to aquifers | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Processing | Production | Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc) | Equipment failure | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Wells | Work-over | Water sourcing (for injection) | Extracting river water for injection | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Wells | Decomissioning | Decomissioning of reinjection well | NA | Need to know more | [9 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Construction | General waste disposal | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Construction | Potable water | NA | [10 empty] | 0 | 0 | 0 | 0
Processing | Construction | Salt storage | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Construction | Water sourcing (for injection) | Need to know more | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Decomissioning | Access roads and easements (e.g. for drilling rigs and equipment) | Need to know more -see rehabilitation plan | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Decomissioning | Accommodation, administration, workshop, depots, service facilities | NA | [10 empty] | 0 | 0 | 0 | 0
Processing | Decomissioning | Brine storage ponds | Need to know more | [10 empty] | 0 | 0 | 0 | 0
Wells | Decomissioning | Dismantling | NA | [10 empty] | 0 | 0 | 0 | 0
Processing | Decomissioning | Hypersaline brine ponds | Need to know more | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Decomissioning | Potable water | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Decomissioning | Power and communications | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Decomissioning | Pressure concrete | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Decomissioning | Remediation | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Decomissioning | Signage | NA | [10 empty] | 0 | 0 | 0 | 0
Processing | Decomissioning | Treated water pond | Need to know more | [10 empty] | 0 | 0 | 0 | 0
Wells | Decomissioning | Waste disposal | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Exploration and appraisal | Airborne geophysics | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Exploration and appraisal | General waste disposal | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Exploration and appraisal | Geochemistry testing | NA | [10 empty] | 0 | 0 | 0 | 0
Pipelines | Exploration and appraisal | Pipeline route survey | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Exploration and appraisal | Potable water | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Exploration and appraisal | Sewage treatment and disposal | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Exploration and appraisal | Subsurface geophysics | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Exploration and appraisal | Water sourcing (for injection) | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Production | General waste disposal | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Production | Geochemistry testing | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Production | Inspection and well maintenance | NA | [10 empty] | 0 | 0 | 0 | 0
Roads and infrastructure | Production | Potable water | NA | [10 empty] | 0 | 0 | 0 | 0
Processing | Production | Salt storage | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Construction | Construction of reinjection wells and pipes | NA | [10 empty] | 0 | 0 | 0 | 0
Wells | Production | Reinjection of co-produced water into a target aquifer | Need to know more | [10 empty] | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0

## Pivot_table
Impact_Causes | Impact_Mode | Activities
Aquitard leaks | Aquifer depressurisation (non-target, non-reservoir) | Water and gas extraction
Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | Dam failure | Untreated co-produced water storage, processing and disposal (pilot stage only)
| Leaching from storage ponds | Untreated co-produced water storage, processing and disposal (pilot stage only)
| Leaking | Brine storage ponds, pumps and water disposal pipelines
Hypersaline brine ponds
Treated water pond
| Overflow and/or loss of containment | Surface water and mud storage and evaporation
| Surface water contamination | Drill cutting disposal
Waste disposal
Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure); Natural disaster (e.g. bushfire, flooding, earthquake) | Fire | Power generation facility (for processing plant)
Corridor/site vegetation removal | Soil erosion following heavy rainfall | Accommodation, administration, workshop, depots, service facilities
Brine storage ponds, pumps and water disposal pipelines
Construction of access roads and easements (e.g. for drilling rigs and equipment)
Gas and water-gathering pipeline networks (well to processing plant)
Gas compression stations
Gas processing plant
Gas-gathering pipeline networks
Ground-based geophysics
Groundwater monitoring bore construction
Hypersaline brine ponds
Operation access roads and easements (e.g. for drilling rigs and equipment)
Power generation facility (for processing plant)
Pump and well head installation
Site preparation
Temporary Accommodation, administration, workshop, depots, service facilities
Treated water pond
Trunk gas pipelines and associated easements (processing plant to town)
Depressurisation | Subsidence | Water and gas extraction
Diverting site/corridor drain line | Disruption of natural surface drainage | Accommodation, administration, workshop, depots, service facilities
Brine storage ponds, pumps and water disposal pipelines
Construction of access roads and easements (e.g. for drilling rigs and equipment)
Fuel and oil storage facilities
Gas compression stations
Gas processing plant
Gas-gathering pipeline networks
Hypersaline brine ponds
Operation access roads and easements (e.g. for drilling rigs and equipment)
Power generation facility (for processing plant)
Site preparation
Temporary Accommodation, administration, workshop, depots, service facilities
Treated water pond
Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc)
Fault open or opening | Aquifer depressurisation (fault-mediated) | Water and gas extraction
Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation) | Accidental intersection of aquifer | Horizontal drilling
| Accidental intersection of fault | Horizontal drilling
| Changing non-target aquifer properties (physical or chemical) | Hydraulic fracturing
| Contaminate non-target aquifer (chemical) | Hydraulic fracturing
| Fire | Process production plant
| Miss perforation target and connect aquifers through the well | Perforation
| Miss perforation target and depressurise aquifers | Perforation
| Mud and drill cutting spillage | Site clean-up and rehabilitation
| Mud spillage and poor rubbish disposal | Remediation
| Spillage | Fuel and oil storage facilities
Groundwater monitoring bore construction
Materials delivery and storage
Process production plant
Pump and well head installation
| Spillage: e.g. diesel | Accommodation, administration, workshop, depots, service facilities
Fuel and oil
Power and communications
Temporary Accommodation, administration, workshop, depots, service facilities
| Spillage: e.g. of sewage | Sewage treatment and disposal
| Spillage: on site | Materials delivery and storage
| Spillage: prior to dilution on site | Hydraulic fracturing concentrate delivery
Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | Pipe failure | Gas and water-gathering pipeline networks (well to processing plant)
Trunk gas pipelines and associated easements (processing plant to town)
| Pipeline failure | Gas-gathering pipeline networks
Human error, accident (e.g. containment loss, digging, ignition, logging machine fault, formation variation); Natural disaster (e.g. bushfire, flooding, earthquake) | Fire | Fuel and oil storage facilities
Gas and water-gathering pipeline networks (well to processing plant)
Ignition following pipe failure; Natural disaster (e.g. bushfire, flooding, earthquake) | Fire | Gas compression stations
Gas processing plant
Gas-gathering pipeline networks
Trunk gas pipelines and associated easements (processing plant to town)
Inappropriate disposal | Cuttings disposal | Groundwater monitoring bore construction
Inappropriate disposal; Containment failure/leaching/flooding (e.g. lining material failure, loss of holding capacity, pipe failure, dam failure) | Recovered fluid disposal | Drill stem testing (extraction)
Slug testing (injection)
| Spillage and/or inappropriate disposal | Hydraulic fracturing fluid injection and disposal
Incidental to vegetation removal and compaction in pipeline corridor | Disruption of natural surface drainage | Gas and water-gathering pipeline networks (well to processing plant)
Trunk gas pipelines and associated easements (processing plant to town)
Incomplete grouting | Incomplete/compromised cementing/casing (linking aquifers) | Groundwater monitoring bore construction
Groundwater monitoring bore construction or expansion
Incomplete reservoir knowledge, too much pressure | Connecting aquifers | Hydraulic fracturing
Inevitable, Deliberate | Aquifer depressurisation (coal seam) | Water and gas extraction
| Changing target aquifer properties (physical or chemical) | Hydraulic fracturing
| Contaminate target aquifer (chemical) | Hydraulic fracturing
| Disruption to natural surface water course (e.g. creek crossing) | Construction of access roads and easements (e.g. for drilling rigs and equipment)
Operation access roads and easements (e.g. for drilling rigs and equipment)
| Reduction in pressure head | Pump testing
| Seal integrity loss | Pressure concrete durability
| Temporary disruption to natural surface water course (e.g. sandbagging a creek to lay pipe) | Gas and water-gathering pipeline networks (well to processing plant)
Trunk gas pipelines and associated easements (processing plant to town)
Interrupting ephemeral water courses | Interruption of natural surface drainage | Ground-based geophysics
Litter, spills | Impacts of ground support staff | Accommodation, administration, workshop, depots, service facilities
Brine storage ponds, pumps and water disposal pipelines
Construction of access roads and easements (e.g. for drilling rigs and equipment)
Fuel and oil storage facilities
Gas and water-gathering pipeline networks (well to processing plant)
Gas compression stations
Gas processing plant
Gas-gathering pipeline networks
Ground-based geophysics
Hypersaline brine ponds
Operation access roads and easements (e.g. for drilling rigs and equipment)
Power generation facility (for processing plant)
Process production plant
Site preparation
Staff movement and activities
Surface core testing
Temporary Accommodation, administration, workshop, depots, service facilities
Treated water pond
Trunk gas pipelines and associated easements (processing plant to town)
Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc)
Number of drilling control issues | Fluid loss to aquifer | Slug testing (injection)
| Imbalance of mud pressure between well and aquifer | Drilling and coring
Drilling and logging
| Localised watertable reduction | Drilling and logging
| Very localised watertable reduction | Drilling and coring
Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Containment failure/leaching/flooding (e.g. lining material failu | Accidental intersection of artesian aquifer | Drilling and coring
Drilling and logging
| Bore leakage between aquifers | Abandonment
| Bore leakage to surface | Abandonment
| Incomplete seal | Pressure concrete completion
| Incomplete/compromised cementing/casing (gas leakage) | Cementing and casing
| Incomplete/compromised cementing/casing (linking aquifers) | Cementing and casing
Poor design, construction, implementation, management (e.g. Abandonment practice, bore location, lack of knowledge, historical data records, sealing practices, geological characterisation); Natural disaster (e.g. bushfire, flooding, earthquake) | Containment failure | Brine storage ponds, pumps and water disposal pipelines
Hypersaline brine ponds
Treated water pond
Production of water | Aquifer depressurisation | Water and gas extraction
(blank) | Accidental intersection of existing bore | Horizontal drilling
| Adds to co-produced water | Water injection
| Aquifer depressurisation (aquitard-absent) | Water and gas extraction
| Aquifer pressurisation (fault-mediated) | Water and gas extraction
| Cement interaction with aquifer (leaching Ca(OH)2) | Cementing and casing
| Cuttings disposal | Groundwater monitoring bore construction or expansion
Groundwater supply bore
| Discharge to river | Untreated co-produced water storage, processing and disposal (pilot stage only)
| Discharge to river (via first or third party) | Treated co-produced water disposal
| Discharge to river following heavy rainfall | Treated co-produced water disposal
Untreated co-produced water storage, processing and disposal (pilot stage only)
| Disruption of natural surface drainage | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Groundwater monitoring bore construction
Groundwater monitoring bore construction or expansion
Groundwater supply bore
Pump and well head installation
Treated co-produced water pipelines and pumps
| Disruption to SW/GW connectivity - due to backfill, soil compaction | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Gas and water-gathering pipeline networks (well to processing plant)
Treated co-produced water pipelines and pumps
Trunk gas pipelines and associated easements (processing plant to town)
| Dust suppression | Construction of access roads and easements (e.g. for drilling rigs and equipment)
Operation access roads and easements (e.g. for drilling rigs and equipment)
| Equipment failure | Gas compression stations
Gas processing plant
Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc)
| Extracting river water for injection | Water sourcing (for injection)
| Extracting river water for shandying | Treated co-produced water disposal
| Groundwater extraction | Groundwater supply bore
| Impacts of ground support staff | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Groundwater monitoring bore construction
Groundwater monitoring bore construction or expansion
Groundwater supply bore
Pump and well head installation
Treated co-produced water pipelines and pumps
| Incomplete removal of concrete base | Process production plant
| Incomplete/compromised cementing/casing (linking aquifers) | Groundwater supply bore
| Increase discharge to rivers following irrigation | Treated co-produced water disposal
| Intersection of GW via directional drilling under river | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Gas and water-gathering pipeline networks (well to processing plant)
Treated co-produced water pipelines and pumps
Trunk gas pipelines and associated easements (processing plant to town)
| NA | Accommodation, administration, workshop, depots, service facilities
Airborne geophysics
Construction of reinjection wells and pipes
Decomissioning of reinjection well
Dismantling
General waste disposal
Geochemistry testing
Inspection and well maintenance
Pipeline route survey
Potable water
Power and communications
Pressure concrete
Remediation
Salt storage
Sewage treatment and disposal
Signage
Subsurface geophysics
Waste disposal
Water sourcing (for injection)
| Need to know more | Brine storage ponds
Hypersaline brine ponds
Reinjection of co-produced water into a target aquifer
Treated water pond
Water sourcing (for injection)
| Need to know more -see rehabilitation plan | Access roads and easements (e.g. for drilling rigs and equipment)
| Pipe corossion and leaching | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Gas and water-gathering pipeline networks (well to processing plant)
Treated co-produced water pipelines and pumps
Trunk gas pipelines and associated easements (processing plant to town)
| Pipe failure | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Treated co-produced water pipelines and pumps
| Pressurize gas pipe to remove water plug | Gas and water-gathering pipeline networks (well to processing plant)
| Raise watertable following irrigation | Treated co-produced water disposal
| Reinjection to aquifers | Treated water disposal
| Soil chemistry changes following irrigation | Treated co-produced water disposal
| Soil erosion following heavy rainfall | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Groundwater monitoring bore construction or expansion
Groundwater supply bore
Treated co-produced water pipelines and pumps
Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc)
| Soil salt mobilisation following irrigation | Treated co-produced water disposal
| Spillage | Brine storage ponds, pumps and water disposal pipelines
Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Fuel and oil storage facilities
Gas and water-gathering pipeline networks (well to processing plant)
Gas compression stations
Gas processing plant
Gas-gathering pipeline networks
Groundwater monitoring bore construction or expansion
Groundwater supply bore
Hypersaline brine ponds
Power generation facility (for processing plant)
Treated co-produced water pipelines and pumps
Treated water pond
Trunk gas pipelines and associated easements (processing plant to town)
Water treatment plant (RO, fixed resin, fixed disc, electrochemical, etc)
| Temporary disruption to natural surface water course (e.g. sandbagging a creek to lay pipe) | Fresh water (RO Permeate) pipelines, pumps and reticulation systems (Water leaving processing plant - to external i.e. Town)
Treated co-produced water pipelines and pumps